## Test Case Tracking
Test Cases
TC01 - Homepage - Web Hosting is Active and Set Up
A user should be able to access the PinUp website on his/her own computer or mobile device.
Precondition: the user must have internet access
Assumption: a supported web browser is being used
Test steps:
Navigate to the app webpage: |  | http://ec2-54-85-216-19.compute-1.amazonaws.com/
Expected result: A page displaying the homepage of the PinUp application should be displayed
Pass/Fail? | Pass
TC02 - Sign-up - Authenticate Successfully on App Website
A potential user should be able to successfully sign up, and a confirmation email should be sent to his/her email.
Precondition: the user must have internet access
Assumption: a supported web browser is being used
Test steps:
Navigate to the application homepage
Click the “Sign Up” button at the top right
Enter your Name, Email, DOB, and the Password for your account setup.
Check your email address for an account activation link
Expected result: An email is sent to the user with an account activation link to access his/her dashboard.
Pass/Fail? | Pass
TC03 - Login - Authenticate Successfully on App Website
A registered user should be able to successfully login to his/her account.
Precondition: the user must already be registered with an email address and password
Assumption: a supported web browser is being used
Test steps:
Navigate to the application homepage
Click the “Login” button at the top right
In the “username” field, enter the email of the registered user
In the “password” field, enter the password of the registered user
Click “Sign In”
Expected result: A page displaying the registered users account dashboard is shown with their profile picture, username, posted tasks, etc...
Pass/Fail? | Pass
TC04 - Upload Profile Photo - Add a Profile Picture in Users Account
A registered user should be able to successfully upload a profile picture in their account.
Precondition: the user must be logged into their account.
Assumption: the user is uploading a .png or .jpeg file
Test steps:
Login in to users account
Click the box where an empty or already existing profile picture is shown, on the left side of the dashboard
Click “Browse” to search for the image in your computer that you would like to upload.
Click “Upload Picture” to save it.
Expected result: The uploaded image being displayed as the user's profile picture in their account dashboard.
Pass/Fail? | Pass
TC05 - Add Sub-Account User
A registered user should be able to create sub-accounts in their dashboard. These users will be able to accept posted tasks and receive payment upon completing them.
In order to add sub accounts, the other user has to have an account already or you can invite them through email. However, if the other user is under the age of 13, then all you have to do is provide their first and last name
Precondition: the user must be logged into their account.
Assumption:
Test steps:
Login in to users account
Click the “Add Sub-Account” button on the bottom left side of the dashboard
On the “Register New Account” popup window, enter all of the required fields.
Click “Submit.” You will see the Sub account added to the dashboard.
Expected result: The created sub-account will be added and shown in the dashboard
Pass/Fail? | Pass
TC06 - Remove Sub-Account
A registered user should be able to remove sub-accounts in their dashboard.
Precondition: the user must be logged into their account.
Assumption: there must be an existing sub-account to remove
Test steps:
Login in to account
Click the “View All Partnerships" link in the left side of the dashboard
On the "Partnerships" page, click the pin icon next to the "Delete User?" of the specific sub-account you want to delete
Expected result: The existing sub-account will be removed and not shown in your partnerships list anymore.
Pass/Fail? | Pass
TC07 - Adding a Task as the Sponsor
A registered user should be able to add/post new tasks in their dashboard
Precondition: the user must be logged into their account.
Assumption:
Test steps:
Click the pin icon in the center of the blank task pane in the "Task Board" section
On the “New Task” popup window, enter all of the required fields.
Click the “Submit” button.
The new task will be created, and displayed as available in the task dashboard.
Expected result: A new task will be shown in the users dashboard
Pass/Fail? | Pass
TC08- Editing a Task as the Sponsor
A registered user should be able to edit an existing task on their dashboard
Precondition: the user must be logged into their account.
Assumption: there must be an existing task to edit
Test steps:
Click the “View” link on the appropriate task on the dashboard
On the “Review Task” page, edit the necessary fields.
Click the “Submit” button to save changes.
Expected result: The existing task will be updated to shown the new changes made to its details.
Pass/Fail? | Pass
TC09 - Initiating a Task as a Sub-Account
A sub-account user can accept a task to complete
Precondition: the sub-account user must be logged into their account.
Assumption:
Test steps:
First Option
Email link will be sent to the user to view and accept the task
Click the "Accept" button
Task will now be shown in the users "Accepted Tasks" section of dashboard
Second Option
Log in to your account via the PinUp homepage.
On the upper right hand side of the dashboard, a pin icon will show your pending tasks to accept.
Click on the task you want to accept and on the confirmation page, and then select the "Accept" button
Expected result: The accepted task will be shown in the users dashboard
Pass/Fail? | Pass
TC10 - Canceling a Task as a Sub-Account
A sub-account user can cancel a task they are unable to complete
Precondition: the sub-account user must be logged into their account.
Assumption: the sub-account user must have accepted the particular task already
Test steps:
Log in to your account via the PinUp homepage.
Click the appropriate task in the “Accepted Tasks” section of the dashboard
Click the"Abandon Task" button to mark that you wish to cancel it
Expected result: The task will now be removed from the sub-account users dashboard
Pass/Fail? | Pass
TC11 - Completing a task as a Sub Account
A sub-account can mark a task as completed once they have finished it
Precondition: the sub-account user must be logged into their account.
Assumption: the sub-account user must have accepted the particular task already
Test steps:
Log in to your Sub Account via the PinUp homepage.
Click the appropriate task in the “Accepted Tasks” section of the dashboard
Click the"Completed" button to mark that you have finihsed it
Expected result: The task will now be marked as “Pending” and a confirmation email will be sent to the sponsor. When the sponsor confirms the task is complete, the payout amount will be transferred to the sub-account users Lumens wallet in their account.
Pass/Fail? | Pass
TC12- Cancelling a Task as the Sponsor
An account user can cancel a task they no longer want completed.
Precondition: the account user must be logged into their account.
Assumption: the task should exist in the users dashboard
Test steps:
Click the “View” link on the appropriate task on the dashboard
On the “Review Task” page, click the “Delete” button..
Expected result: The task will now be completely removed from the users dashboard
Pass/Fail? | Pass
TC13 - Approve Payment for Completed Task
Once a sub-account user has completed an assigned chore, the sponsor must approve payout
Precondition: the account user must be logged into their account.
Assumption: the user must have a crypto currency account with Lumens.
Test steps:
First Option
Email link will be sent to the sponsor to approve payout for the task
Click the "Completed" button to approve
Second Option
Log in to your account via the PinUp homepage.
Click on the link that says ""Payouts Requesting Approval," on the left side of the dashboard, underneath the profile picture.
Select the task you want to approve payout for
Click the "Completed" button to approve
Expected result: The amount agreed upon for completing the chore will be transferred to the users account who completed it.
Pass/Fail? | Pass
TC14 - Assigning a Payout Amount to a Task
The account user can specify how much their task will pay upon its completion.
Precondition: the account user must be logged into their account.
Assumption: the user(s) must have a crypto currency account with Lumens.
Test steps:
Click the pin icon in the center of the blank task pane in the "Task Board" section
On the “New Task” popup window, enter all of the required fields.
Enter the amount of Lumens the particular task should be worth.
Click the “Submit” button.
Expected result: If the assigned amount is greater than the Lumen amount in the sponsor’s available Wallet, the prompt will not allow you to finish editing the Task until the amount is fixed. Also, When you are done editing the task, the amount will be removed from your available wallet, but kept in your total balance.
Pass/Fail? | Pass
TC15 - Logging Out
The user should be able to successfully log out of their account
Precondition: the user must already have an account
Assumption: the user must be logged into their account.
Test steps:
Click the “Logout” button in the upper right of the dashboard page.
Expected result: It will redirect the user to the homepage, where they can login again.
Pass/Fail? | Pass
TC16 - Incorrect Login
The user should be sent an email to their registered email address if password is forgotten
Precondition: the user must already have an account
Assumption: the user has attempted to login in with a password
Test steps:
Click the “Login” button at the top right
Enter invalid password
Click the button to unlock account
Enter the email address of the account to which the password reset link will be sent to.
Expected result: an email will be sent to the user with password reset link
Pass/Fail? | Pass
TC17 - Password Recovery
The user should be sent an email to their registered email address if password is forgotten
Precondition: the user must already have an account
Assumption: the user has attempted to login in with a password
Test steps:
Click the “Login” button at the top right
In the login form, select the "Forgot Password" Option
Enter the email address of the account to which the password reset link will be sent to.
Expected result: an email will be sent to the user with password reset link
Pass/Fail? | Pass

## Detailed Test Case Tracking
Test Case # | Module Name | Applicable Role | Description | Results
TC01 | Homepage | Account holders/ Subaccount holders | A user should be able to access the PinUp website on his/her own computer or mobile device.
|  |  | With internet access and a desktop computer/laptop, navigate to the PinUp webpage: https://pinup-tasks.herokuapp.com/ | Pass
TC02 | Sign-up | Account holders/ Subaccount holders | Should be able to sign-up on PinUp webpage, and receive a comfirmation with a valid email addres. Enter:
|  |  | - Name | Pass
|  |  | - Email | Pass
|  |  | - DOB | Pass
|  |  | - Password | Pass
|  |  | - Received email activation link | Pass
TC03 | Login | Acct holders/Subacct holders/Devs | Should be able to successfully login to his/her account. Navigate to PinUp homepage and:
|  |  | - Click on the"Login" button at the top right | Pass
|  |  | - In the "username" field, enter a valid email address of a registered account holder. | Pass
|  |  | - In the "pasword" field, enter the password of the registered account holder. | Pass
|  |  | - Click on the "Sign In" button | Pass
TC04 | Upload Profile Photo | Acct holders/Subacct holders/Devs | Should be able to successfully upload a profile picture in their account.
|  |  | - Login to registered account | Pass
|  |  | - Click the box where an empty or already existing profile picture is shown, on the left side of the dashboard | Pass
|  |  | - Click “Browse” to search for the image in your computer that you would like to upload | Pass
|  |  | Click “Upload Picture” to save it. | Pass
TC05 | Add Sub-Account User | Acct holders/Developers | A registered user should be able to create sub-accounts in their dashboard.
These users will be able to accept posted tasks and receive payment upon completing them.
The subaccount user has to have an account already or you can invite them through email.
If subaccount user is below the age of 13, then only first and last name are required.
|  |  | - Login in to users account | Pass
|  |  | - Click the “Add Sub-Account” button on the bottom left side of the dashboard | Pass
|  |  | - On the “Register New Account” popup window, enter all of the required fields. | Pass
|  |  | - Click “Submit.” You will see the Sub account added to the dashboard. | Pass
TC06 | Remove Sub-Account | Acct holders/Developers | A registered user should be able to remove sub-accounts in their dashboard.
|  |  | - Login in to account | Pass
|  |  | - Click the “View All Partnerships" link in the left side of the dashboard | Pass
|  |  | - On the "Partnerships" page, click the pin icon next to the "Delete User?" of the specific sub-account you want to delete | Pass
|  |  | - The sub account will no longer be available, and will be removed from your partnerships list | Pass
TC07 | Adding a Task as Sponsor | Acct holders/Developers | A registered user should be able to add and post new tasks in their dashboard
|  |  | - Click the pin icon in the center of the blank task pane. | Pass
|  |  | - On the “New Task” popup window, enter all of the required fields. | Pass
|  |  | - Click the “Submit” button. | Pass
|  |  | - The new task will be created, and displayed as available in the task dashboard. | Pass
TC08 | Editing a Task as Sponsor | Acct holders/Developers | A registered user should be able to edit an existing task in their dashboard
|  |  | - Click the “View” link on the appropriate task on the dashboard | Pass
|  |  | - On the “Review Task” page, edit the necessary fields. | Pass
|  |  | - Click the “Submit” button to save changes. | Pass
TC09 | Initiating a task as Sub-Account | Acct holders/Developers | A sub-account user can accept a task to complete.
First Option
|  |  | - Email link will be sent to the user to view and accept the task | Pass
|  |  | - Click the "Accept" button | Pass
|  |  | - Task will now be shown in the users "Accepted Tasks" section of dashboard | Pass
Second Option
|  |  | - Log in to your account via the PinUp homepage. | Pass
|  |  | - On the upper right hand side of the dashboard, a pin icon will show your pending tasks to accept. | Pass
|  |  | - Click on the task you want to accept and on the confirmation page, and then select the "Accept" button | Pass
TC10 | Canceling a Task as Sub-Account | Subacct holders/Developers | A sub-account user should be able to cancel their assigned task if they unable to complete
|  |  | - Log in to your account via the PinUp homepage. | Pass
|  |  | - Click the appropriate task in the “Accepted Tasks” section of the dashboard to view it | Pass
|  |  | - Click the"Abandon Task" button to mark that you wish to cancel it | Pass
|  |  | - The task will now be removed from the “Accepted Tasks” section of the users dashboard | Pass
TC11 | Completing a Task as Sub-account | Subacct holders/Developers | A sub-account user should be to complete their assigned task
|  |  | - Log in to your Sub Account via the PinUp homepage. | Pass
|  |  | - Click the appropriate task in the “Accepted Tasks” section of the dashboard to view it | Pass
|  |  | - Click the"Completed" button to mark that you have finihsed it | Pass
TC12 | Cancelling Task as Sponsor | Acct holders/Developers | An account user should be able to change the status of a task
|  |  | - Click the “View” link on the appropriate task on the dashboard | Pass
|  |  | -On the “Review Task” page, click the “Delete” button.. | Pass
TC13 | Approve Payment for Completed Task | Acct holders/Developers | An account user should be able to add Lumens to account balance.
First Option
|  |  | - Email link will be sent to the sponsor to approve payout for the task | Pass
|  |  | - Click the "Completed" button to approve | Pass
Second Option
|  |  | - Log in to your account via the PinUp homepage. | Pass
|  |  | - Click on the link that says ""Payouts Requesting Approval," on the left side of the dashboard, underneath the profile picture. | Pass
|  |  | - Select the task you want to approve payout for | Pass
|  |  | - Click the "Completed" button to approve | Pass
TC14 | Assigning a Payout Amount to Task | Acct holders/Developers | The account user can specify how much their task will pay upon its completion.
|  |  | - Click the pin icon in the center of the blank task pane in the "Task Board" section | Pass
|  |  | - On the “New Task” popup window, enter all of the required fields. | Pass
|  |  | - Enter the amount of Lumens the particular task should be worth. | Pass
|  |  | - Click the “Submit” button. | Pass
TC15 | Loggin Out | Acct holders/Developers | The user should be able to successfully log out of their account
|  |  | - Click the “Logout” button in the upper right of the dashboard page. | Pass
TC16 | Incorrect Login | Acct holders/Developers | The user should be sent an email to their registered email address if password is forgotten
|  |  | - Click the “Login” button at the top right | Pass
|  |  | - Enter invalid password | Pass
|  |  | - Click the button to unlock account | Pass
|  |  | - Enter the email address of the account to which the password reset link will be sent to. | Pass
TC17 | Password Recovery | Acct holders/Developers | The user should be sent an email to their registered email address if password is forgotten
|  |  | - Click the “Login” button at the top right | Pass
|  |  | - In the login form, select the "Forgot Password" Option | Pass
|  |  | - Enter the email address of the account to which the password reset link will be sent to. | Pass

## BugsIssues
Bug/Defect | Date Found | Assigned Engineer | Resolved? | Resolution Details | Resolution Code
Grid layout becomes altered on smaller screens, i.e. mobile devices and tablets. | 2018-04-15 | Nabeel Hussain | Yes | Researched bootstrap library to determine proper use of grid layout. Added “col-lg-4” and “col-sm-12” classes to each column of the grid in order to cause the element to occupy full screen on small displays and only a third of the display on larger ones. | Code Error
Unresponsive buttons on homepage. | 2018-04-15 | Xavier Davis | Yes | Scoured source code to find ineffective HTML statements regarding button reference and associated Javascript. | Code Error
Configuration management and code integration difficulty. Since we had multiple people coding different parts of the app, we ran into some problems on getting everyones code to seamlessly fit together. | 2018-04-15 | Xavier Davis | Yes | We decided to have 1 person be in charge of overseeing the final code and committing it to the live production version. This way multiple people were not altering the live code, leading to unforeseen issues and errors. | Change Request/Next Release
Unresponsive Navigation Bar Links | 2018-04-22 | Xavier Davis | Yes | Used Firefox’s Inspect Elements tool to troubleshoot the issue. The browser tool reviled one of the JavaScript libraries included a DOM event that rendered navigation bar links unresponsive. By removing the function from the imported JavaScript library, the navigation bar links redirected the user as expected. | Code Error
Storing and Retrieving Profile Images | 2018-04-22 | Xavier Davis | Yes | Using npm to install formidable, the back-end express server was able to parse the HTML form to retrieve the image file uploaded from the user. Once retrieved the image file was converted into binary for storage into the MongoDB document. Retrieving the image for display required converting the base64 binary data stream into a String value. By adding data:image/jpeg;base64 in the HTML image tag’s source attribute, the binary file can be converted into a readable String for the application to display. | Code Error
Server configuration file was altered and would not redirect port 80 request to the listening express server. | 2018-04-29 | Xavier Davis | Yes | After multiple attempts of manually adjusting the file, the nginx proxy would not defualt to the underlying express server to render the proper application files. As an option we re-built the entire server and wiped all files, but the proxy redirect still did not occur. So, finally we switched the server hosting services to Heroku. We were able to launch an Node.js instance within minutes and deploy the application code seamlessly. | Environment Build Problem
Server was slowing and crashing when multiple users were on it at the same time. | 2018-05-01 | Xavier Davis | Yes | We were able to kick back up an AWS server, and we finally learned how to get the reverse proxy to work. The server will also now auto restart if it crashes, so no more 404 Error messages. It is running on multiple CPUs as opposed to only 1 like we were doing before. | Environment Build Problem

## Risk Register
PRE - MITIGATION |  |  | PRE - MITIGATION |  |  |  | RESIDUAL RISK POST MIGATION
Risk ID | Risk Description | Probability | Impact | Overall scores | Response | Person Initial | Probability | Impact | Overall score
1 | Risks involving Database
1.1 | Application may be slow in performance | Fairly Likely | Low | 6 | Increased database (Mongo DB) capcity | FK | Fairly Likely | Low | 3
2 | Risks involving Server
2.1 | Availabilty (Single point of failure) | Unlikely | Low | 3 | Redundancy | FK | Very Ulikely | Low | 1
3 | Risks involving GUI
3.1 | Code Injection | Likely | High | 20 | Prepaired statements | FK | High | Low | 8
3.2 | Unauthorized access | Very Likely | High | 20 | Cookies to activate firewalls | FK | High | Low | 7